## Recruitment Timeline Planner
UC Irvine DFA Human Resources
Recruitment Timeline Planner
This is a planner to help you anticipate recruitment timeframes for career positions (excluding temp and student roles) based on the exisiting UCI DFA process.
Instructions: 1. Enter your recruitment start date (date your position request was approved) in cell C7. 2. Timeline dates will automatically update downstream. 3. Modify duration days in column C as needed. 4. Predicted candidate start dates will show in cells 26D and 26E (depending on candidate's notice period).
Task | Owner | Duration (Days) | Start Date | End Date
Intake Meeting with HRBP / Position Approval | Supervisor with HRBP | 5 | 2026-08-01 | 2026-08-05
Position Request Form | Supervisor, Cabinet Member
30 Day Hold Period & Recruitment Preparation |  | 30 | 2026-08-06 | 2026-09-04
• Update Job Description • attend new Interview Training (if applicable) • Select Committee Members • Complete MIBT courses (if incomplete) • Place calendar holds for screening and interviews • Hold Committee Charge Meeting • Develop Screening Questions • Develop Interview Questions • Select Additional Advertisements (if needed)
Initial Posting Period | HRBP (or Recruiter based on level) | 14 | 2026-09-05 | 2026-09-18
Screen Initial Applicant Pool | Supervisor/ Committee | 5 | 2026-09-19 | 2026-09-23
First Round Interviews | Supervisor/ Committee | 5 | 2026-09-24 | 2026-09-28
Second / Final Round Interviews | Supervisor/ Committee | 6 | 2026-09-29 | 2026-10-04
Candidate Selection & Reference Checks | Supervisor/ Committee | 5 | 2026-10-05 | 2026-10-09
Offer Stage | Supervisor/ Compensation | 6 | 2026-10-10 | 2026-10-15
• Allow 2-3 days for response time • Possible additional time for negotiation or approvals
Candidate Notice Period / Start Date | Central HR, DFA HR, Payroll, Supervisor | 28 | 2026-10-16 | 2026-11-12
• Allow 2 - 4 weeks notice for start time, dependent on position grade, relocation or other factors.
Start Date Preparation? (background check, etc)
Formulas:
End Date = [Start Date]+[Duration (Days)]-1